LUMIÈRE

EVENT ASSET & LOGISTICS REPORT

| EVENT REFERENCE EVT-2026-00072 | GENERATED September 18, 2026 | STATUS COMPLETED |
| --- | --- | --- |

1. EVENT INFORMATION

| EVENT NAME Annual Corporate Gala 2026 | CLIENT ABC Corporation | VENUE Grand Ballroom | EVENT TYPE Corporate |
| --- | --- | --- | --- |
| EVENT DATE September 20, 2026 | EVENT TIME 6:00 PM – 11:00 PM | EXPECTED GUESTS 250 | EVENT STATUS Completed |
| EVENT COORDINATOR [Coordinator Name] | VENUE CONTACT [Contact Name] | CREATED August 4, 2026 | LAST UPDATED September 21, 2026 |

2. EVENT OVERVIEW

A corporate appreciation event featuring stage styling, guest tables, decorative displays, lighting elements, and customized event installations.

3. ASSET SUMMARY

| 42 PLANNED | 42 DEPLOYED | 40 RETURNED | 1 DAMAGED | 1 MISSING / LOST | 0 PENDING |
| --- | --- | --- | --- | --- | --- |

4. ASSETS DEPLOYED

| ASSET | CLASS | PLANNED | DEPLOYED | RETURNED | DAMAGED | LOST | STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Aurora Lighting Kit | Lighting | 6 | 6 | 6 | 0 | 0 | COMPLETE |
| Marlow Lounge Chair | Furniture | 8 | 8 | 8 | 1 | 0 | REVIEW |
| Oak Plinth Set | Display | 16 | 16 | 15 | 1 | 0 | DEFICIT |
| Signature Drape Panel | Décor | 12 | 12 | 12 | 0 | 0 | COMPLETE |

5. LOGISTICS INFORMATION

DISPATCH

September 20, 2026 — 8:00 AM   —   Warehouse → Loading

↓

TRANSIT

September 20, 2026 — 9:15 AM   —   In Transit

↓

INGRESS

September 20, 2026 — 10:10 AM   —   Arrived at Venue

↓

SETUP

September 20, 2026 — 11:00 AM   —   Setup Completed

↓

EVENT

September 20, 2026 — 6:00 PM   —   Event Started

↓

EGRESS

September 21, 2026 — 12:15 AM   —   Post-Event Inspection

↓

RETURN

September 21, 2026 — 2:00 AM   —   Assets Returned

TRANSPORT INFORMATION

| VEHICLE Truck 02 | DRIVER [Driver Name] | DISPATCH Sept 20, 2026 — 8:00 AM |
| --- | --- | --- |
| VENUE ARRIVAL Sept 20, 2026 — 10:10 AM | RETURN Sept 21, 2026 — 2:00 AM | CREW [Names / Team] |

6. INGRESS

| DISPATCH LOADING STATUS Confirmed | ITEMS DISPATCHED 42 | ITEMS RECEIVED 42 |
| --- | --- | --- |
| VENUE ARRIVAL 10:10 AM | RECEIVING STATUS Confirmed | SETUP HANDOFF 10:20 AM |
| EXCEPTIONS None |  |  |

7. ON-SITE / SETUP

| SETUP START 10:20 AM | SETUP COMPLETION 11:00 AM | CREW [Names] |
| --- | --- | --- |
| ASSETS STAGED 42 / 42 | EXCEPTIONS None | ON-SITE STATUS Completed |

8. EGRESS & RETURN

| POST-EVENT INSPECTION Completed | EXPECTED RETURN QTY 42 | ACTUAL RETURN QTY 40 |
| --- | --- | --- |
| DAMAGED 1 | MISSING / LOST 1 | EGRESS TIMESTAMP Sept 21, 2026 — 12:15 AM |
| RETURN TIMESTAMP Sept 21, 2026 — 2:00 AM | RETURN STATUS Requires Review |  |

9. ASSET RECONCILIATION

| METRIC | QUANTITY |
| --- | --- |
| Planned | 42 |
| Deployed | 42 |
| Returned | 40 |
| Damaged | 1 |
| Lost / Missing | 1 |
| Pending Verification | 0 |

10. DEFICIT / EXCEPTIONS

| ASSET Oak Plinth Set | EXPECTED 16 | RETURNED 15 | DEFICIT 1 |
| --- | --- | --- | --- |

STATUS   Investigation Required

11. CREW & RESPONSIBILITY

| EVENT COORDINATOR [Coordinator Name] | CREW LEAD [Crew Lead Name] | DISPATCH CREW [Names] | SETUP CREW [Names] |
| --- | --- | --- | --- |
| EGRESS CREW [Names] | DRIVER [Driver Name] | VENUE CONTACT [Contact Name] | VEHICLE Truck 02 |

12. AUDIT & VERIFICATION

| EVENT REFERENCE ID EVT-2026-00072 | REPORT REFERENCE RPT-2026-00072 |
| --- | --- |
| GENERATED BY System (Lumière) | GENERATED TIMESTAMP September 18, 2026 — 09:42 AM |
| LAST SYNCHRONIZATION September 21, 2026 — 2:05 AM | LAST MODIFIED September 21, 2026 — 2:05 AM |
| VERIFIED BY [Verifier Name] | VERIFICATION STATUS Verified |

| [ QR ] | SCAN TO VERIFY EVENT RECORD Ref: EVT-2026-00072 |
| --- | --- |

This report is a system-generated record of the Lumière event asset lifecycle and is provided for internal operations, accountability, and archival purposes.